## Risk Register
☁ NimbusTech Solutions — Information Security Risk Register
Document Version: 1.0 ¦ Last Updated: March 24, 2026 ¦ Framework: ISO 31000 / NIST RMF ¦ Classification: INTERNAL
Risk ID | Description | Category | Likelihood (1-5) | Impact (1-5) | Risk Score (L × I) | Rating | Mitigation Measures | Owner | Residual Risk (1-5) | Review Date
R-001 | Data Breach via External Attacker | Cybersecurity | 4 | 5 | 20 | HIGH | Encrypt data at rest & in transit; deploy WAF; enable CloudTrail logging; conduct quarterly pen tests. | CTO | 2 | 2025-06-30
R-002 | Phishing Attack on Employees | Cybersecurity | 4 | 4 | 16 | HIGH | Mandatory phishing-awareness training; deploy email filtering (DMARC/DKIM/SPF); enforce MFA on all accounts. | IT Lead | 2 | 2025-06-30
R-003 | Misconfigured S3 Bucket (Public Exposure) | Cloud / Infra | 3 | 5 | 15 | MEDIUM | Enforce S3 Block Public Access at org level; use AWS Config rules; IaC templates with policy guardrails. | DevOps Lead | 1 | 2025-07-31
R-004 | Credential Reuse / Weak Passwords | IAM | 4 | 4 | 16 | HIGH | Enforce SSO + MFA; deploy password manager; automated account lockout after 5 failed attempts. | IT Lead | 2 | 2025-06-30
R-005 | Insider Threat (Malicious or Negligent) | People & Process | 2 | 5 | 10 | MEDIUM | Principle of least privilege; off-boarding checklist; monitor privileged-access logs; NDA & AUP agreements. | HR / CTO | 2 | 2025-09-30
R-006 | Third-Party / SaaS Supply Chain Attack | Vendor Risk | 3 | 4 | 12 | MEDIUM | Vendor security assessments; limit OAuth scopes; review third-party CVEs monthly; contractual SLAs. | CTO | 2 | 2025-07-31
R-007 | Ransomware / Malware Infection | Cybersecurity | 3 | 5 | 15 | MEDIUM | Immutable off-site backups (3-2-1 rule); EDR on all endpoints; network segmentation; IR playbook. | IT Lead | 2 | 2025-06-30
R-008 | Cloud Service Outage (AWS/GCP Downtime) | Availability | 3 | 4 | 12 | MEDIUM | Multi-AZ deployments; failover runbooks; SLA monitoring; architect for graceful degradation. | DevOps Lead | 2 | 2025-09-30
R-009 | Unpatched Vulnerabilities in Dependencies | Cloud / Infra | 4 | 3 | 12 | MEDIUM | Automated SCA scanning in CI/CD (Dependabot/Snyk); enforce patch SLA: Critical ≤ 7 days. | DevOps Lead | 2 | 2025-07-31
R-010 | Insufficient Logging & Monitoring | Compliance | 3 | 3 | 9 | MEDIUM | Centralize logs in SIEM (CloudWatch + Splunk); define alerting thresholds; review dashboards weekly. | IT Lead | 1 | 2025-07-31
R-011 | Regulatory / GDPR Non-Compliance | Legal / Compliance | 2 | 5 | 10 | MEDIUM | Appoint DPO; conduct annual GDPR audit; maintain ROPA; privacy-by-design in SDLC. | CEO / Legal | 2 | 2025-12-31
R-012 | DDoS Attack on Public Endpoints | Availability | 2 | 4 | 8 | LOW | CloudFront + AWS Shield Standard; rate limiting; auto-scaling; incident runbook for traffic spikes. | DevOps Lead | 1 | 2025-09-30

## Heat Map
☁ NimbusTech Solutions — Risk Heat Map
Risk Score = Likelihood × Impact ¦ 🟥 HIGH (≥16) 🟧 MEDIUM (9-15) 🟨 ELEVATED (4-8) 🟩 LOW (1-3)
Impact ↑ / Likelihood →
| L=1 | L=2 | L=3 | L=4 | L=5
I=5 | 5 | 10 R-005 R-011 | 15 R-003 R-007 | 20 R-001 | 25
I=4 | 4 | 8 R-012 | 12 R-006 R-008 | 16 R-002 R-004 | 20
I=3 | 3 | 6 | 9 R-010 | 12 R-009 | 15
I=2 | 2 | 4 | 6 | 8 | 10
I=1 | 1 | 2 | 3 | 4 | 5
Legend: | HIGH ≥16 | MEDIUM 9-15 | ELEVATED 4-8 | LOW 1-3

## Summary Dashboard
☁ NimbusTech Solutions — Risk Summary Dashboard
Total Risks | HIGH Risks | MEDIUM Risks | LOW Risks
12 | 3 | 8 | 1
Top 5 Risks by Score
Risk ID | Description | Score | Rating | Owner | Review Date
R-001 | Data Breach via External Attacker | 20 | HIGH | CTO | 2025-06-30
R-002 | Phishing Attack on Employees | 16 | HIGH | IT Lead | 2025-06-30
R-004 | Credential Reuse / Weak Passwords | 16 | HIGH | IT Lead | 2025-06-30
R-003 | Misconfigured S3 Bucket (Public Exposure) | 15 | MEDIUM | DevOps Lead | 2025-07-31
R-007 | Ransomware / Malware Infection | 15 | MEDIUM | IT Lead | 2025-06-30